# School Sport New Zealand

# 2023 Event Health & Safety Plan Template

# The completion of an Event Health & Safety Plan is a requirement of ALL School Sport NZ sanctioned events agreed to by event organisers in their sanctioning application. Event Health & Safety Plans must be submitted 6 weeks prior to the event date to the School Sport NZ Administrator, office@schoolsportnz.org.nz .These will be posted on the School Sport NZ website for principals who will then determine if they send students to an event.

- The preparation and submission of the Event Health & Safety Plan is the responsibility of the Event Organiser and must include;

  - Event Safety Plan – details of risk management associated with the specific event

  - Sport Specific Safety Plan – details of risks inherent in the specific sport. The NSO responsible for your sport should be able to supply you with this.

  - Venue Safety Plan – including emergency evacuation procedures. The management of the venue you are using should be able to supply you with this.

- This template may assist you in identifying risks and developing appropriate actions to mitigate these when developing an Event Health & Safety Plan. However if you have a plan in an alternative format you are welcome to submit that providing it covers the required material in 2 above.

- This document should be completed with reference to;

- Health and Safety Guidance for School Sport – Ministry of Education 2016

- School Sport NZ Event Health & Safety System

SECTION 1: Event Information

| Event Name: South Island Satellite Indoor Volleyball Cup | This Plan Dated: 9/2/23 |
| --- | --- |
| Event Location | Pioneer Stadium & Cowles Stadium |
| Event Date | 28-30 March 2023 |
| Organisation delivering event | Canterbury Volleyball Association |
| Number of Participants | Approx 300 |
| Number of Schools Participating | Approx 20 |

## Event overview. Provide a brief summary of what your event will involve.

The South Island Satellite Tournament provides a fantastic opportunity for schools that are not in the top tier of the South Island schools competition, or that do not have the funds to travel to the National Tournament, a chance to compete at a tournament with similar skilled teams.  All skill levels are accepted as we run many divisions across the boys and girls competitions, without those teams that have travelled to school National Tournament.

SECTION 2: Event Personnel.

| Event Personnel: List key event personnel, roles and contacts – some suggestions have been made here but you may alter to suit your event as appropriate. Vulnerable Children’s Act: Event organisers must ensure that events comply with the requirements of the VCA. Indicate below any of the core roles where Police Vetting of personnel has been completed under VCA requirements or state NA if VCA does not require this. |
| --- |
| Name | Role | Responsibility | Qualifications or Experience | Contact Details | VCA status NA or Police Vetted |
| Malcolm Taylor | Event Manager | Overall responsibility | CVA Operations Manager | 0276838606 om@cva.nz | Police Vetted |
| Malcolm Taylor | Volunteer Coordinator | Volunteer recruitment, training & management |  |  |  |
| Malcolm Taylor | Officials Coordinator | Recruitment, training & management |  |  |  |
| Malcolm Taylor | Health and Safety Officer | Risk assessments, legal compliance, site inspections, first aid |  |  |  |
| CCC Pioneer & Cowles Staff | Welfare | Toilets and wash facilities |  |  |  |
| CCC Pioneer & Cowles Staff | Waste Management | Waste clearance and recycling |  |  |  |
| Malcolm Taylor | Disputes & Discipline | Convening & Chairing disputes panel |  |  |  |

## SECTION 3: Risk Assessments and Management

You can use the guide below to assess risk levels in completing your Event Risk Assessment. The template on the following page will guide you.

| Likelihood | Consequence |
| --- | --- |
|  | Insignificant | Minor | Moderate | Major | Critical |
| Almost Certain | Medium | Medium | High | Extreme | Extreme |
| Likely | Low | Medium | High | High | Extreme |
| Possible | Low | Medium | High | High | High |
| Unlikely | Low | Low | Medium | Medium | High |
| Rare | Low | Low | Low | Low | Medium |

| Consequence | Description of Consequence | Likelihood | Description of Likelihood |
| --- | --- | --- | --- |
| 1. Insignificant | No treatment required | 1. Rare | Will only occur in exceptional circumstances |
| 2. Minor | Minor injury requiring First Aid treatment (e.g. minor cuts, bruises, bumps) | 2. Unlikely | Not likely to occur within the foreseeable future, or within the project lifecycle |
| 3. Moderate | Injury requiring medical treatment or lost time | 3. Possible | May occur within the foreseeable future, or within the project lifecycle |
| 4. Major | Serious injury (injuries) requiring specialist medical treatment or hospitalisation | 4. Likely | Likely to occur within the foreseeable future, or within the project lifecycle |
| 5. Critical | Loss of life, permanent disability or multiple serious injuries | 5. Almost Certain | Almost certain to occur within the foreseeable future or within the project lifecycle |

| Assessed Risk Level | Description of Risk Level | Actions |
| --- | --- | --- |
|  | Low | If an incident were to occur, there would be little likelihood that an injury would result. | Undertake the activity with the existing controls in place. |
|  | Medium | If an incident were to occur, there would be some chance that an injury requiring First Aid would result. | Additional controls may be needed. |
|  | High | If an incident were to occur, it would be likely that an injury requiring medical treatment would result. | Controls will need to be in place before the activity is undertaken. |
|  | Extreme | If an incident were to occur, it would be likely that a permanent, debilitating injury or death would result. | Consider alternatives to doing the activity. Significant control measures will need to be implemented to ensure safety. |

Control the Risk: Use the template on the following page;

- List the hazards/risks you have identified.

- Rate their risk level (refer to information above to assist with this).

- Detail the appropriate control measures you will implement to control the risk.
Note: Control measures should be implemented in accordance with the preferred hierarchy of control.

| Hierarchy of Controls - |
| --- |
| Most effective (High level) Least effective (Low level) | Elimination: remove the hazard completely from the workplace or activity |
|  | Substitution: replace a hazard with a less dangerous one (e.g. a less hazardous chemical) |
|  | Engineering control: making an event safer separate people from the hazard (e.g. safety barrier) |
|  | Administration: putting rules, signage or training in place to make the event safer (e.g. induction, route plan, safety training) |
|  | Personal Protective Equipment (PPE): Protective clothing and equipment (e.g. helmets, mouth guards, PFD’s) |

I

## 3A: Event Risk Assessment & Management Plan

| Event Hazard Identification and Risk Assessment |
| --- |
| Hazard or Risk identified. | Risk Level | Level of Control (see previous page) | Action |
| What could go wrong? | Low Med High Extreme | Eliminate | Substitute | Engineer control | Admin Control | PPE | How will we prevent it? | Person responsible | What we will do if it happens? |
| COVID exposure | High | no | no | yes | yes | yes | Message schools participating re good hygiene standards and ask them to stay clear if unwell Hand sanitiser available throughout venues Game protocols may change/evolve depending on the situation, CPF setting ie timed games | Event Manager | Isolate athlete/team not feeling well Contact school/team management and ensure they follow tournament and school protocols |
| Heat exhaustion | Med | No | No | Yes | Yes | Yes | Proper clothing, Event schedules Fans within gyms | Event Manager | Refer to onsite first aid |
| Gastro bug | Med | No | No | Yes | Yes | Yes | Enforce precautions and reminders in pre-event materials and during the event | Event Manager | Follow health and safety procedures, hand washing, hand sanitizer available |
| Injury accident in the proximity of the venue | Low | No | No | Yes | No | No | Awareness of traffic management around the venue | Event Manager | Support victims, schools, use local medical facilities |
| Equipment malfunction | Med | No | No | Yes | Yes | No | Check equipment prior to the event, check equipment periodically throughout the day. Notification of any issues | Event Manager | Equipment will be onsite to ensure repairs can be made if required |
| Toilet / water facilities not working | Med | No | No | Yes | No | No | Ensure the venue has checked all their facilities are working well and there are alternatives in place | Event Manager in liaison with Venue Mgrs | Utilize alternative buildings and their toilet / water facilities |

3B: Sport Specific Risk Assessment & Management Plan – you may have already included the risks specific to your sport in the Event Risk Assessment above. If you have not done so, please provide a risk assessment specific to the hazards in your sport here OR if your NSO has supplied you with a Sport Specific Risk Assessment & Management Plan, please attach it to this document.

| Sport Specific Risk Assessment |
| --- |
| Hazard or Risk identified. | Risk Level | Level of Control (see previous page) | Action |
| What could go wrong? | Low Med High Extreme | Eliminate | Substitute | Engineer control | Admin Control | PPE | How will we prevent it? | Person responsible | What we will do if it happens? |
| Concussion | Med | No | No | No | Yes | Yes | Referees will all be safety trained. Ensure that there is safety padding on poles and referee stands. | Team Manager Event Manager | Refer to onsite first aid |
| Ankle sprain, bruises | Med | No | No | No | Yes | No | Players to wear protective gear for ankles and elbows if needed; rake sand/ make it even as possible. | Team official First Aider | Refer to onsite first aid/ physio; make sure ice packs are provided. |
| Muscle cramps | Med | No | No | No | Yes | No | Provide enough warm up time for players. | Team officials First Aider | Referees will stop the game and ensure that the player is safe. Time will be given to first aider/ team officials to stretch the player or move the player out of the court. |
| Muscle strains | Med | No | No | No | Yes | No | Provide enough warm-up time for players; physio will tape areas that may be prone to the strain/ sprain, or where chronic pain occurs. | Team officials First Aider | Referees will stop the game and ensure that the player is safe. Time will be given to first aider/ team officials to stretch the player or move the player out of the court |
| Fracture | High | No | No | No | Yes | No | There may be no prevention if it is self-inflicted during game time. | First Aider Medic | Provide first aid and call an ambulance. |
| Dehydration/ Heat Exhaustion/ Heat Stroke | Med | No | No | No | Yes | No | Make sure there is proper ventilation and water fountains are working properly. Also provide shaded areas and cool playing surface with water. | Event Manager | Provide players with water, ice pack and cool towels. Allow player to recover in a cooler place. |

3B: Venue Safety Plan – including Emergency Evacuation Procedures. Please attach a copy of the Venue Safety plan to this document. The Venue Management will be able to supply you with this.

SECTION 4: Core Provisions and Communications.

| Core Provisions: Please give details of the following core provisions as they apply to your event or state NA if they do not apply |
| --- |
| Item. | Provider | Person Responsible | Contact | Management Notes |
| First Aid and Medical services | Pioneer Stadium Christchurch Hospital Pegasus 24hr surgery Physio South Pioneer Sports Med Garden City Dental | Malcolm Taylor to provide contacts to participants | 02768386060 om@cva.nz |  |
| Drinking water | Reserved to taps within stadium area | Participants |  |  |
| Food | Pioneer Café Barrington Mall Fresh Choice Barrington | Participants |  |  |
| Shade | CVA, but not necessary game activity will be inside | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Toilets | Pioneer Stadium | Participants |  |  |
| Event Security | CVA, Selwyn Sports Centre & Christchurch City Council | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Waste Management | CVA, Selwyn Sports Centre & Christchurch City Council | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Spectator Controls | CVA & Christchurch City Council | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Parking | Christchurch City Council | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Vehicles onsite | CVA | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Event Insurance | CVA | Malcolm Taylor | 02768386060 om@cva.nz |  |
| Media | CVA | Malcolm Taylor | 02768386060 om@cva.nz |  |

| Event Communications Plan. Please give details of the following as they apply to your event. |
| --- |
| Communication Item | Person Responsible | Audience | When? | Notes – eg Content |
| Pre Event Info – to schools, participants | Malcolm Taylor | Schools / Coaches / Managers / students / families | 3 Weeks before the event | Event manual, registration, bond |
| Event Briefing – Safety Briefing, Event info for students, coaches, managers | Malcolm Taylor | Coaches / Managers | Via email prior to the event, alongside tournament procedures | Health and safety, officials, draws, game protocol conducted on morning of Tournament |
| Event Day Communications – Cancellations, changes, weather | Malcolm Taylor | Coaches / Managers | Through email / text as appropriate | As appropriate |
| Emergency Communications - evacuation, lost person, emergency services, notification to schools/parents/media | Malcolm Taylor | Schools / Coaches / Managers / students / families | Email / text / facebook as appropriate | As appropriate |
| Media information | Malcolm Taylor | Schools / Community / Family / Athletes | Print media / Email / text / facebook Prior, during post event | Stories and angles to promote the game |
| Post event reporting | Malcolm Taylor | School Sport NZ Volleyball NZ | Post event as required | Reporting templates as required |

Please submit this plan to the School Sport NZ Administrator, office@schoolsportnz.org.nz 6 weeks prior to the event date.

# Text boxes

Where an Event Health & Safety Plan has still not been received 2 weeks prior to an event, School Sport NZ will withdraw the sanction form the event and advise schools not to attend.